## Sheet1
date | Project Name | Failure mode | Product Type | affect range | description | Priority | Owner | analysis | root cause | Containment action | Corrective Action | disposal of product | status | attachment
2015-06-17 | PQE | Wrong label | EDR | all EDR product | label description not match Agile | Major | Brad Qiu | The operator found the label was dirty after printing, and there is no label rework station in MES, and then operator used the manual format(which not locked) to reprint the label. | 1. The label format (Bartender) was not locked which created by engineer. 2. There was no label rework station in MES. | 1. Review other EDR product label in warehouse: 1pcs label ink missing failed among 166pcs in total. And then the failed label reworked via MES. - Done 6/25 Doris | 1. Added label rework station into MES system. - Done 6/18 Fang Zhou 2. The label format has been locked; operator can only adjust label position. – Done 6/18 Fang Zhou 3. Review other label format are OK. - Done 6/18 Yongtang Quan 4. Ask related engineer to delete the manual format to prevent the similar occurring in the future. – Done 6/19 Fang Zhou 5.Add the locked Bartender requirement to PM check list, ECO 129122. - Done 8/10/2015 Doris 6. GRR for VMI and OQC operator. Passed. - Done 7/6/2015 Doris OQC: Kappa is 0.9479 VMI: Kappa is 0.8148 | rework via MES system | closed
2015-06-18 | PQE | VCSEL crack | EDR | 48 pcs VCSEL | Prodution line found 48 pcs VCSEL crack at EQ_Bootloader station | Minor | Brad Qiu | In April 2015, production line return the 1175823 document with C00 Version to DDC for some unknown reason, and the operator has no reference document at the moment. So after 1175823 updated, the DDC no longer issued the updated document to production line. | Different criteria between IQC and OP because of operator did not have related inspection document. | 1. IQC double confirmed the “defect” material, and align the updated criteria with production operator. - Done 6/19/2015 Yingying Liu | 2. In June 19 2015, DDC issued the C01 version document to production line and arranged related training for operator. - Done 6/23/2015 Hellen (DDC) 3. Confirmed other station whether they have same document problem. - Done 6/23/2015 Qianqian Su | release | closed
2015-06-25 | PQE | change color for cable | EDR | all production line | There are two colors of cable in OQC inspection station at the same time | Critical | Brad Qiu | PLM said that customer insist EDR cables color must different from QDR/FDR cables. | PLM make all EDR cables Aqua and all QDR/FDR cables orange. And PLM did not want to issue PCN to other customers. | 1. Warehouse: follow FIFO principle, no urgently dispatch. - start 7/9/2015 Lucy 2. Production line: add color description to VMI station record. - start7/1 Lixiu 3. Delivery：Specified data code to delivery as VMI station record- weekly review in production weekly meeting. - Done 9/10 Lucy | 1.Next time PM must raise a new PN or use other method to avoid issue like this when material changed. - Owner: Mark Zhao | release | closed
2015-06-30 | PQE | OBA function fail in EDR | EDR | 7pcs | In June, there are 7 pcs OBA function fail among 493 pcs, and 5 pcs failure mode is Rxbert at low temperature. | Critical | Brad Qiu | analysis by Wen Wu in R&D lab | IC glitch of QTIA1B caused the OBA failure. Switch QTIA1B to QTIA1C, The trial run lot of samples with QTIA1C is under test. Monitor two months, no OBA fail in OQC OBA test. - Done 9/17 Wen | 100% OBA test | 1.00C~700C cable, risk is lower since room temperature is covered, release. - Done 7/2 Lucy 2. Update OBA test spec file to add temperature configuration as 200C. - Done7/2 Fang 3. 200C~700C cable, 3M/5pcs and 10M/5pcs rework: 1st OBA test@200C - Done7/2 Fang =>all cables passed OBA test@200C – Inventory release. 4. Keep these 3M/5pcs and 10M/5pcs samples to do verification at (150C, 200C and 700C) on engineer mode: no failure was found at 150C and 200C, these parts had been returned to production to go through normal procedure. - Done 7/8 Fang 5.5pcs (DTS01WD, DTR01SE, DTR01ST, DTR01SD, DTR01SM) OBA function fail. Root cause： | release products which passed all testing process | closed
2015-07-02 | PQE | PD pad lift off | EDR | wafer trace ID 3528-40-50, 8046pcs in total | Production line found PD pad lift off when Wire bonding with PD(1182345),DC(R150413867);Failure rate is 1.02% | Critical | Brad Qiu | 1. R150413867 has the higher failure rate 1.02% with pad lift off compared to other data code PD. 2. Check the WB parameter as usual: USG is 85mA; Time is 15ms; Force is 16g. 3. Wire Pull is 8.2g in the good product. | PD raw material problem | stop build with affected PD | 1. Feedback and send lift off samples to Alen for further analysis. -Done 9/1 Eva Allen reply: “Even though not desirable, the void between dielectric layer is not the cause of delamination. The delamination happens between semiconductor and the first dielectric, not between dielectric layers. More likely cause of delamination is less-than-adequate wirebond parameters” 2. Purge the rest material, and RTV to Allen. - Done 7/12Eva | release good prosucts | closed
2015-09-11 | PQE | OBA failed with no power in OQC | C-wire Gen2 |  | 3 Pcs OBA fail were found in OQC in August 2015. Retest other parts with same batch in production line – all pass. | Major | Brad Qiu | Analyzed by Jean, Harry and Leon support. - On-going Jean Jin |  | For WIP 1. Add 100% power check after final assembly - start from 9/18 Leon 2. Add 100% power check before packing - start from 9/18 Leon 3. Add 100% Bert test after packing - start from 9/18 Albert 4. OBA sampling plan change form C=0, AQL=4.0 to C=0, AQL=1.0, OQC performed on 9/16. - Done 9/16 Doris For inventory finish goods Rework with action 2 and action3. - start from 9/18 Albert | Design fixture to ensure the cable well assembled in final assembly. - Start 9/16 Harry | release good products | open

## Sheet2
1166757 | EDR1-1512-0820NFG | EF20151218-03 | F15121900331 | shipped
1166757 | EDR1-1512-0744NFG | EF20151209-01 | F15122000025 | shipped
1166757 | EDR1-1512-0820NFG | EF20151219-04 | F15122000029 | stock
1166757 | EDR1-1512-0820NFG | EF20151218-03 | F15122000040 | shipped
1166757 | EDR1-1512-0820NFG | EF20151219-04 | F15122000041 | stock
1166757 | EDR1-1512-0820NFG | EF20151219-04 | F15122000124 | stock
1166757 | EDR1-1512-0820NFG | EF20151219-04 | F15122000125 | stock
1166757 | EDR1-1512-0820NFG | EF20151219-04 | F15122000126 | stock
1166757 | EDR1-1512-0820NFG | EF20151219-04 | F15122100083 | stock
1166757 | EDR1-1512-0820NFG | EF20151218-03 | F15122100087 | stock
1166757 | EDR1-1512-0820NFG | EF20151219-05 | F15122100092 | stock
1166756 | EDR1-1512-0821NFG | EF20151220-02 | F15122100509 | stock
1166758 | EDR1-1512-0823NFG | EF20151221-01 | F15122200106 | stock
1166757 | EDR1-1512-0820NFG | EF20151219-07 | F15122200109 | stock
1166757 | EDR1-1512-0820NFG | EF20151219-04 | F15122200121 | stock
1166758 | EDR1-1512-0823NFG | EF20151221-01 | F15122200131 | stock
1166758 | EDR1-1512-0823NFG | EF20151221-01 | F15122200596 | 未入库
1166758 | EDR1-1512-0823NFG | EF20151221-01 | F15122200597 | 未入库
1166753 | EDR1-1512-0822NFG | EF20151221-03 | F15122200598 | 未入库
1166757 | EDR1-1512-0820NFG | EF20151222-01 | F15122200599 | 未入库